# Annual Goals & Study Timeline

Review Period: 2026

Role: Senior ML Engineer

Focus: Production excellence, platform-level impact, and technical leadership in AI/ML systems

# At a Glance

## Annual Goals

| # | Goal Area | Key Outcome | Success Looks Like |
| --- | --- | --- | --- |
| 1 | Production Excellence — Smart Scheduler | Stable production system with business KPIs | Beta to GA, SLAs defined, monitoring live, cost optimized |
| 2 | LLM/RAG Systems — Technical Depth | Eval framework + advanced retrieval in production | RAGAS pipeline running, 2+ RAG algorithms benchmarked, re-ranking integrated |
| 3 | Infrastructure & Data Ownership | End-to-end IaC + data transformation | Terraform CI/CD, dbt project with tests, zero manual infra changes |
| 4 | Platform Thinking — Reusable Frameworks | Components other teams can adopt | Shared eval library, Terraform modules, internal best-practices doc |
| 5 | Cross-Team Collaboration | Business use cases driven end-to-end | 1+ new use case scoped with stakeholders, results presented to leadership |
| 6 | Technical Leadership | Team capability multiplier | 2+ knowledge shares, 1+ engineer mentored, engineering standards proposed |
| 7 | Continuous Technical Growth | Structured depth across 5 areas | Tangible artifact per area (code, benchmark, doc, or deployed infra) |

## Study Plan

| Phase | Topics | Weeks | Hours | Key Artifact |
| --- | --- | --- | --- | --- |
| 1 | LLM/RAG Evaluation | Weeks 1-4 | ~30h | End-to-end eval pipeline + LangSmith tracing |
| 2 | Advanced RAG Algorithms | Weeks 5-8 | ~32h | 4+ algorithms prototyped and benchmarked |
| 3 | Re-Ranking Methods | Weeks 9-10 | ~15h | Re-ranking integrated with latency/quality report |
| 4 | dbt on AWS | Weeks 11-12 | ~12h | dbt project running on Snowflake with tests passing |
| 5 | Terraform | Weeks 13-16 | ~28h | DC-Copilot infra fully in Terraform + CI/CD |
| 6 | Integration & Mock Interviews | Weeks 17-18 | ~15h | Can whiteboard all topics at senior level |
|  | Total | ~18 weeks | ~132h | ~10h/week (1-1.5h weekdays + 2-3h weekends) |

# 1. Production Excellence — Smart Scheduler

Objective: Deliver Smart Scheduler as a stable, production-grade system with measurable business impact.

Transition Smart Scheduler from beta to full production release with defined SLAs (availability, latency, error rate)

Establish production monitoring and alerting (latency P50/P95/P99, error budgets, throughput dashboards) to ensure system reliability meets enterprise standards

Define and track key business KPIs tied to Smart Scheduler (e.g., scheduling accuracy improvement, reduction in manual scheduling effort, time-to-resolution)

Conduct load testing and capacity planning to validate system behavior under peak traffic conditions

Implement cost tracking per inference call and optimize resource utilization to reduce per-request cost by a measurable margin

Own the full incident response lifecycle — root cause analysis, remediation, and post-mortem documentation for any production issues

Deliver a production readiness review document covering observability, failover, data integrity, and rollback procedures

# 2. LLM/RAG Systems — Technical Depth & Innovation

Objective: Establish deep, demonstrable expertise in LLM evaluation and advanced retrieval systems, applied directly to production workloads.

Design and implement a comprehensive RAG evaluation framework covering retrieval quality (Context Precision, Recall, MRR, NDCG), generation quality (Faithfulness, Answer Relevancy, BERTScore), and end-to-end correctness (RAGAS suite, LLM-as-a-Judge)

Evaluate and integrate at least two advanced RAG algorithms (e.g., Hybrid Search, Corrective RAG, RAG Fusion) into production retrieval pipelines with before/after benchmarks

Implement a re-ranking layer (Cross-Encoder or equivalent) and measure its impact on retrieval precision and downstream answer quality

Build automated regression detection for RAG quality — drift monitoring that flags degradation across evaluation metrics week-over-week

Produce an internal technical document or knowledge-share on "Advanced RAG Patterns: What Works and What Doesn't" based on hands-on experimentation

# 3. Infrastructure & Data Ownership

Objective: Own the infrastructure and data transformation layer end-to-end, ensuring reproducibility, auditability, and operational maturity.

Define and manage all application infrastructure using Terraform — covering compute (ECS/Fargate), networking (VPC, security groups), storage (S3, DynamoDB), secrets (Secrets Manager, Parameter Store), and AI services (OpenSearch Serverless)

Implement Terraform CI/CD integration with automated plan on pull requests and controlled apply on merge, including security scanning (tflint, checkov)

Build and maintain a dbt project for data transformation — staging models, tested marts, incremental materializations — integrated with Snowflake on AWS

Establish data quality gates using dbt tests (schema validation, referential integrity, freshness checks) as part of the data pipeline

Ensure all infrastructure changes are peer-reviewed, version-controlled, and auditable — no manual console changes in production environments

# 4. Platform Thinking — Reusable Frameworks & Components

Objective: Move beyond project-level delivery to build reusable components that accelerate the team and adjacent teams.

Extract and package the RAG evaluation framework as a reusable internal library or shared service that other teams can adopt for their own LLM workloads

Design a standardized LLM observability stack (tracing, token usage tracking, latency breakdowns per pipeline node) that can be adopted across multiple AI applications

Create Terraform modules for common AI/ML infrastructure patterns (vector database setup, LLM serving infra, async processing queues) that reduce setup time for new projects

Document and publish internal best practices for production LLM systems — covering evaluation, retrieval, re-ranking, monitoring, and cost management

Identify at least one opportunity to generalize a DC-Copilot component into a shared capability (e.g., intent classification service, document ingestion pipeline, streaming response framework)

# 5. Cross-Team Collaboration & Business Impact

Objective: Drive end-to-end business use cases by partnering with product, operations, and engineering teams beyond the immediate ML team.

Partner with at least one business stakeholder team to identify and scope a new use case for the Smart Scheduler or DC-Copilot platform — from problem definition through deployment

Lead technical design discussions with cross-functional teams, translating business requirements into measurable ML system specifications

Present Smart Scheduler production results (business KPIs, system performance, lessons learned) to engineering leadership and non-technical stakeholders

Actively participate in architecture reviews for adjacent systems where ML/AI integration is being considered — provide technical guidance on feasibility, tradeoffs, and recommended patterns

Establish a feedback loop with end users (e.g., maintenance technicians, operations managers) to inform model improvements and feature prioritization

# 6. Technical Leadership & Knowledge Multiplication

Objective: Operate as a technical multiplier — elevating the team's capabilities, not just individual output.

Conduct at least two internal knowledge-sharing sessions (lunch-and-learn, tech talk, or written deep-dive) on topics such as RAG evaluation, Terraform patterns, or production LLM operations

Mentor at least one junior or mid-level engineer through a technical project — provide guidance on system design, code quality, and production readiness

Contribute to the team's engineering standards by proposing and documenting at least one new standard or convention (e.g., evaluation baseline requirements, infrastructure-as-code policy, LLM safety checklist)

Participate in on-call rotations and lead incident response for ML systems, building team-wide operational maturity

Proactively identify technical debt or reliability risks in existing systems and propose prioritized remediation plans with clear business justification

# 7. Continuous Technical Growth

Objective: Deepen expertise in areas that directly enhance the quality and scope of delivered work.

Complete structured study across five technical areas, with hands-on implementation tied to production systems:

| Area | Scope | Application |
| --- | --- | --- |
| LLM/RAG Evaluation | RAGAS, BERTScore, G-Eval, LLM-as-Judge, Drift Detection | Eval framework for DC-Copilot and Smart Scheduler |
| Advanced RAG | Hybrid Search, CRAG, Graph RAG, RAG Fusion, Agentic RAG | Retrieval quality improvements in production |
| Re-Ranking | Cross-Encoder, Cohere Rerank, RRF, FlashRank | Precision gains in document retrieval |
| dbt on AWS | Models, tests, incremental materializations, Snowflake | Data transformation and quality for analytics |
| Terraform | Modules, remote state, CI/CD, AWS provider (IAM, VPC, ECS) | Full infrastructure ownership |

Each area concludes with a tangible artifact: working code, benchmark report, internal doc, or deployed infrastructure

Share key learnings with the broader team through documentation or presentations — ensuring growth translates into team capability

Note: These goals are designed to reflect end-to-end ownership, measurable business outcomes, and technical leadership at a level that drives organizational impact beyond individual projects.

# Study Timeline & Gap Closure Plan

Goal: Master LLM Evaluation, Advanced RAG, Re-Ranking, DBT, and Terraform

Baseline: Working knowledge of Python, ML fundamentals, AWS, and basic RAG (built DC-Copilot)

Daily budget: 1-1.5 hours on weekdays, ~2-3 hours on weekends (~10h/week)

# Summary

| Phase | Topics | Weeks | Hours |
| --- | --- | --- | --- |
| 1 | LLM/RAG Evaluation Metrics | 4 weeks | ~30h |
| 2 | Advanced RAG Algorithms | 4 weeks | ~32h |
| 3 | Re-Ranking Methods | 2 weeks | ~15h |
| 4 | DBT (Data Build Tool) on AWS | 2 weeks | ~12h |
| 5 | Terraform (IaC) | 4 weeks | ~28h |
| 6 | Integration & Mock Interviews | 2 weeks | ~15h |
| Total |  | ~18 weeks (~4.5 months) | ~132h |

# Phase 1: LLM & RAG Evaluation (Weeks 1-4, ~30h)

## Weeks 1-2 — Classical & Embedding-Based Metrics

| Session | Topic | What to Do | Time |
| --- | --- | --- | --- |
| W1-D1 | Why Eval Matters (1.1) | Read section, note DC-Copilot gaps | 1h |
| W1-D2 | Eval Taxonomy (1.2) | Map 3 layers (Retrieval/Generation/E2E) to DC-Copilot | 1h |
| W1-D3 | BLEU (1.3) | Read theory + run nltk example | 1h |
| W1-D4 | ROUGE (1.4) | Run rouge-score on DC-Copilot outputs | 1h |
| W1-D5 | BLEU vs ROUGE | Compare scores on same response pairs, write notes | 1h |
| W1-WE | METEOR (1.5) + BERTScore (1.6) | Compare all 4 metrics on 5 DC-Copilot responses | 2.5h |
| W2-D1 | Perplexity (1.7) | Read theory, understand when it applies | 1h |
| W2-D2 | RAGAS Framework (1.8) | Install RAGAS, run first evaluate() call | 1h |
| W2-D3 | Faithfulness (1.9) | Create test cases with known hallucinations | 1h |
| W2-D4 | Answer Relevancy (1.10) | Test on off-topic vs on-topic responses | 1h |
| W2-D5 | Context Precision (1.11) | Evaluate retrieval ranking quality at k=4, 8 | 1h |
| W2-WE | Context Recall (1.12) + Relevancy (1.13) | Full RAGAS suite on 10 DC-Copilot examples | 2.5h |

Checkpoint: Can explain each metric, run RAGAS programmatically, interpret scores.

## Weeks 3-4 — Advanced Eval, Production & Custom Metrics

| Session | Topic | What to Do | Time |
| --- | --- | --- | --- |
| W3-D1 | Answer Correctness (1.14) | Build 20-row eval dataset with ground truth | 1h |
| W3-D2 | Answer Similarity (1.15) | Expand dataset to 50 rows, test similarity | 1h |
| W3-D3 | Human Eval (1.16) | Read frameworks (Likert, A/B, rubric-based) | 1h |
| W3-D4 | LLM-as-a-Judge (1.17) | Implement GPT-4 judge scoring rubric | 1.5h |
| W3-D5 | Custom Metrics (1.18) | Build part-number-validation metric | 1h |
| W3-WE | Comparison Table (1.19) + Pipeline (1.20) | Write full eval script in a notebook | 2.5h |
| W4-D1 | Precision@K, Recall@K, MAP (1.21) | Add IR metrics to eval pipeline | 1h |
| W4-D2 | G-Eval (1.22) | Implement chain-of-thought evaluation | 1h |
| W4-D3 | SelfCheckGPT (1.23) | Test reference-free hallucination detection | 1h |
| W4-D4 | Toxicity (1.24) + Observability (1.25) | Read + note what applies to DC-Copilot | 1h |
| W4-D5 | Drift Detection (1.26) | Understand regression monitoring patterns | 1h |
| W4-WE | Eval Tools (1.27) + LangSmith | Set up LangSmith tracing for DC-Copilot | 2.5h |

Checkpoint: End-to-end eval pipeline running, can discuss all metrics in an interview.

# Phase 2: Advanced RAG Algorithms (Weeks 5-8, ~32h)

## Weeks 5-6 — Core RAG Patterns

| Session | Topic | What to Do | Time |
| --- | --- | --- | --- |
| W5-D1 | RAG Recap (2.1) | Map DC-Copilot's current architecture | 1h |
| W5-D2 | Naive vs Advanced (2.2) | Identify failure modes from the 7 listed | 1h |
| W5-D3 | Sentence Window (2.3) — theory | Read algorithm, understand window sizing | 1h |
| W5-D4 | Sentence Window (2.3) — code | Prototype with LlamaIndex on sample docs | 1.5h |
| W5-D5 | Parent-Child (2.4) — theory | Understand hierarchical chunking | 1h |
| W5-WE | Parent-Child (2.4) — code | Build page/paragraph/sentence hierarchy, test | 2.5h |
| W6-D1 | Hybrid Search (2.5) — theory | Understand vector + BM25 fusion | 1h |
| W6-D2 | Hybrid Search (2.5) — code | Write OpenSearch hybrid query for DC-Copilot | 1.5h |
| W6-D3 | HyDE (2.6) | Read + implement hypothetical doc generation | 1.5h |
| W6-D4 | Self-Query / Metadata (2.7) | Build metadata-aware retrieval | 1.5h |
| W6-D5 | Review W5-6 | Re-run eval pipeline on each variant, compare | 1h |
| W6-WE | Hands-on comparison | Benchmark Sentence Window vs Parent-Child vs Hybrid | 2.5h |

## Weeks 7-8 — Advanced & Agentic RAG

| Session | Topic | What to Do | Time |
| --- | --- | --- | --- |
| W7-D1 | Corrective RAG (2.8) — theory | Understand relevance grading + fallback | 1h |
| W7-D2 | Corrective RAG (2.8) — code | Implement in LangGraph with grading node | 1.5h |
| W7-D3 | Adaptive RAG (2.9) | Map DC-Copilot's intent routing as adaptive RAG | 1h |
| W7-D4 | Graph RAG (2.10) — theory | Understand knowledge graphs + multi-hop | 1h |
| W7-D5 | Graph RAG (2.10) — code | Build small asset/component/part graph | 1.5h |
| W7-WE | RAG Fusion / Multi-Query (2.11) | Add query variation generation, test recall | 2.5h |
| W8-D1 | Agentic RAG (2.12) | Review DC-Copilot as agentic RAG, note gaps | 1h |
| W8-D2 | PageIndex / Vectorless (2.13) | Evaluate for manual lookups | 1h |
| W8-D3 | Comparison Matrix (2.14) | Fill comparison table from experiments | 1h |
| W8-D4 | DC-Copilot improvement plan | Write "top 3 RAG upgrades" recommendation | 1h |
| W8-D5 | Review | Revisit weakest algorithm, re-read + re-code | 1h |
| W8-WE | Final benchmarks | Run eval pipeline across all variants | 2.5h |

Checkpoint: 4+ RAG algorithms prototyped and benchmarked, clear DC-Copilot upgrade path.

# Phase 3: Re-Ranking Methods (Weeks 9-10, ~15h)

| Session | Topic | What to Do | Time |
| --- | --- | --- | --- |
| W9-D1 | Why Re-Ranking (3.1), Two-Stage (3.2) | Read theory, bi-encoder vs cross-encoder | 1h |
| W9-D2 | Cross-Encoder (3.3) — theory | Understand scoring mechanism | 1h |
| W9-D3 | Cross-Encoder (3.3) — code | Implement ms-marco-MiniLM re-ranker | 1.5h |
| W9-D4 | Cohere Rerank (3.4) | Test Cohere API on DC-Copilot queries | 1h |
| W9-D5 | ColBERT (3.5) | Read late-interaction approach, compare | 1h |
| W9-WE | Benchmark | Cross-Encoder vs Cohere vs ColBERT on same queries | 2.5h |
| W10-D1 | LLM-Based Re-Ranking (3.6) | Implement pointwise LLM scoring | 1h |
| W10-D2 | RRF (3.7) | Implement Reciprocal Rank Fusion | 1h |
| W10-D3 | Custom Scoring (3.8) + FlashRank (3.9) | Enhance SimpleMetrics, test FlashRank | 1.5h |
| W10-D4 | Lost-in-Middle (3.10) + Comparison (3.11) | Position reordering, fill comparison matrix | 1h |
| W10-D5 | Best Practices (3.12) | Finalize re-ranking strategy for DC-Copilot | 1h |

Checkpoint: Re-ranking integrated, latency/quality tradeoffs documented.

# Phase 4: DBT on AWS (Weeks 11-12, ~12h)

| Session | Topic | What to Do | Time |
| --- | --- | --- | --- |
| W11-D1 | What is DBT (4.1) | Read, install dbt-core + dbt-snowflake | 1h |
| W11-D2 | DBT on AWS (4.2) | Set up project with profiles.yml | 1h |
| W11-D3 | Models + Sources (4.3) | Write staging models for work_orders, assets | 1.5h |
| W11-D4 | Seeds + Snapshots (4.3) | Create seed file, write a snapshot | 1h |
| W11-D5 | Tests + Macros (4.3) | Add unique/not_null tests, custom macro | 1h |
| W11-WE | Materializations (4.3) | table vs view vs incremental tradeoffs | 2h |
| W12-D1 | DBT + Snowflake (4.4) | Build marts: work order metrics, asset health | 1.5h |
| W12-D2 | DBT + Redshift (4.5) | Redshift patterns (sort keys, dist keys) | 1h |
| W12-D3 | Do's/Don'ts (4.6) + docs | Run full pipeline, review docs site | 1h |

Checkpoint: dbt project running, dbt test + dbt run passing.

# Phase 5: Terraform (Weeks 13-16, ~28h)

## Weeks 13-14 — Terraform Fundamentals

| Session | Topic | What to Do | Time |
| --- | --- | --- | --- |
| W13-D1 | IaC concepts | Terraform vs CloudFormation vs Pulumi | 1h |
| W13-D2 | Install + first apply | terraform init/plan/apply a basic S3 bucket | 1h |
| W13-D3 | HCL syntax, providers | Write TF for DC-Copilot's S3 buckets | 1h |
| W13-D4 | Resources + data sources | Add DynamoDB table + SQS queue | 1h |
| W13-D5 | Variables + outputs | Parameterize with variables.tf and tfvars | 1h |
| W13-WE | Locals + tfvars per env | Set up sandbox/dev/prod variable files | 2h |
| W14-D1 | State management — local | Understand state file structure | 1h |
| W14-D2 | State management — remote | S3 backend + DynamoDB lock table | 1.5h |
| W14-D3 | terraform import | Import an existing AWS resource into state | 1h |
| W14-D4 | Modules — theory | Understand inputs, outputs, composition | 1h |
| W14-D5 | Modules — code | Refactor into storage + compute + networking | 1.5h |
| W14-WE | Workspaces + lifecycle | Multi-env deployment, prevent_destroy | 2h |

## Weeks 15-16 — Advanced Terraform + DC-Copilot Infra

| Session | Topic | What to Do | Time |
| --- | --- | --- | --- |
| W15-D1 | IAM roles + policies | Write ECS task role + execution role | 1.5h |
| W15-D2 | IAM — assume_role | OpenSearch serverless access policy | 1h |
| W15-D3 | VPC + subnets | Terraform VPC (public + private subnets) | 1.5h |
| W15-D4 | Security groups + endpoints | Lock down traffic for OpenSearch + Snowflake | 1h |
| W15-D5 | ECS/Fargate — task def | Define DC-Copilot API container | 1h |
| W15-WE | ECS/Fargate — service + ALB | Deploy behind load balancer with health checks | 2.5h |
| W16-D1 | Secrets Manager + Param Store | Terraform all DC-Copilot secrets | 1h |
| W16-D2 | CI/CD — terraform plan | Add plan step to PR workflow | 1.5h |
| W16-D3 | CI/CD — terraform apply | Add apply step on main branch merge | 1h |
| W16-D4 | tflint + checkov | Run security scanning on DC-Copilot infra | 1h |
| W16-D5 | Full review | terraform plan entire stack, verify clean | 1h |
| W16-WE | Polish | Fix warnings, add missing tags, clean up | 2h |

Checkpoint: DC-Copilot infra fully in Terraform, deployable via CI/CD.

# Phase 6: Integration & Mock Interviews (Weeks 17-18, ~15h)

| Session | Focus | What to Do | Time |
| --- | --- | --- | --- |
| W17-D1 | System Design prep | Draw production RAG system: eval + retrieval + infra | 1.5h |
| W17-D2 | Coding from memory | Implement eval pipeline from scratch | 1.5h |
| W17-D3 | Coding from memory | Write a Terraform module from scratch | 1.5h |
| W17-D4 | Verbal explanations | Practice explaining RAGAS, re-ranking, DBT out loud | 1h |
| W17-D5 | DC-Copilot case study | Prepare 15-min "How I'd improve DC-Copilot's RAG" | 1.5h |
| W17-WE | Mock interview #1 | System design: "Design a RAG eval platform" | 2h |
| W18-D1 | Review weak spots | Revisit lowest-confidence topics | 1h |
| W18-D2 | Cheat sheet | Finalize 1-page-per-topic summary cards | 1h |
| W18-D3 | Mock interview #2 | Walk through deploying an ML system with Terraform | 1.5h |
| W18-D4 | Mock interview #3 | How do you evaluate and monitor RAG in production? | 1.5h |
| W18-D5 | Final confidence check | Go through 44-topic checklist, flag gaps | 1h |

Checkpoint: Can whiteboard and discuss all topics confidently at senior level.

# Quick Reference: Topic Inventory (44 topics)

## LLM/RAG Evaluation (27 topics)

Evaluation Taxonomy (3 layers)

BLEU Score

ROUGE (ROUGE-1, ROUGE-2, ROUGE-L)

METEOR

BERTScore

Perplexity

RAGAS Framework (install + run)

Faithfulness / Groundedness

Answer Relevancy

Context Precision

Context Recall

Context Relevancy

Answer Correctness

Answer Semantic Similarity

MRR and NDCG

Human Evaluation Frameworks

LLM-as-a-Judge

Custom Domain Metrics

Building an Eval Pipeline

Precision@K, Recall@K, Hit Rate, MAP

G-Eval

SelfCheckGPT & Semantic Entropy

Toxicity & Safety Scoring

Production Observability Metrics

Drift Detection & Regression Monitoring

Eval Tools (LangSmith, DeepEval, LangFuse)

CI/CD Eval Integration

## Advanced RAG (13 topics)

Naive vs Advanced RAG (failure modes)

Sentence Window Retrieval

Parent-Child (Hierarchical) Retrieval

Hybrid Search (Vector + BM25 + RRF)

HyDE (Hypothetical Document Embeddings)

Self-Query / Metadata Filtering

Corrective RAG (CRAG)

Adaptive RAG

Graph RAG

RAG Fusion / Multi-Query RAG

Agentic RAG

PageIndex (Vectorless RAG)

Algorithm Selection & Comparison

## Re-Ranking (10 topics)

Two-Stage Retrieval Paradigm

Cross-Encoder Re-Ranking

Cohere Rerank API

ColBERT Re-Ranking

LLM-Based Re-Ranking

Reciprocal Rank Fusion (RRF)

Custom Scoring Functions

FlashRank / Lightweight Re-Rankers

Lost-in-the-Middle Reordering

Re-Ranking Strategy Selection

## DBT (6 topics)

DBT Core Concepts (models, sources, seeds, snapshots)

Tests & Macros

Materializations (table, view, incremental, ephemeral)

DBT + Snowflake on AWS

DBT + Redshift

DBT Best Practices & CI/CD

## Terraform (10 topics)

HCL Syntax & Core Workflow (init/plan/apply)

Providers, Resources, Data Sources

Variables, Outputs, Locals

State Management (remote backend, locking)

Modules (structure, registry, composition)

Workspaces & Multi-Environment

AWS Provider (IAM, VPC, ECS, Secrets)

Import & Drift Detection

CI/CD Integration (GitHub Actions)

Security Scanning (tflint, checkov)

# Weekly Rhythm

| Day | Time | Activity |
| --- | --- | --- |
| Monday-Friday | 1 hour/day | Read + small code exercise |
| Saturday | 1.5-2 hours | Hands-on coding / prototyping |
| Sunday | 1-1.5 hours | Review + notes + cheat sheet update |
| Total | ~10 hours/week |  |

# Study Tips

1 topic = 1 session — Don't cram 2 topics into one hour; depth beats breadth

Code every other day — Alternate: Day 1 read theory, Day 2 implement it

DC-Copilot is your interview story — Tie every topic back to a real example

Weekend = hands-on — Weekdays for reading, weekends for coding

Keep a cheat sheet — One page per topic: what, why, when, DC-Copilot example

Don't skip Phase 6 — Mock interviews are where knowledge becomes confidence

Generated: 2026-03-18 | Pace: ~10h/week | Estimated completion: ~18 weeks (~4.5 months)